## WAPA Asphalt Design Competition
2012 WAPA Asphalt Design Competition
The WAPA Mix Design Competition has evolved into the WAPA Asphalt Design Competition. The
WAPA Asphalt Design Competition expands the asphalt engineering beyond just the HMA mix
design to also include pavement structure design and project management engineering. The
competition consists of establishing a pavement construction scope, determining a pavement
structure, developing a HMA mix design, planning out the construction process and summarizing
all of this engineering into a unit price and project cost estimate that your project team is
submitting as a construction bid (Design-Build concept).
Currently there is not a National Competition with a similar structure, so WAPA has modified
the competition award structure.
| 1st Place | $2000 to the Team*
| 2nd Place | $1000 to the Team*
$200 to each other Team*
*A team must earn a minimum of 75 points
to be eligible for prize earnings.
The competition is open to the following schools:
Marquette University
Michigan Technical University
University of Wisconsin - Madison
University of Wisconsin - Milwaukee
University of Wisconsin - Platteville
The competition team can be composed of undergraduates and graduate students.
The competition team is limited to a maximum of 5 members.
2012 competition aggregate materials were supplied by Payne & Dolan.
The competition format requires the submission of HMA superpave gyratory compaction specimens,
gyratory compaction data, a written report and PowerPoint presentation and a "live" presentation
to the competition judges via web conferencing and conference calling.

## Scoring
2012 WAPA Asphalt Pavement Design Competition
Scoring
Pavement Structural Design
|  | Technical Content | 10
|  | Written Report & Presentation | 5
|  | Presentation Question Responses | 5
|  | Subtotal | 20 | pts
Job Mix Formula Design
|  | Technical Content | 30
|  | Written Report & Presentation | 10
|  | Presentation Question Responses | 10
|  | Subtotal | 50 | pts
Construction Management
|  | Technical Content | 20
|  | Written Report & Presentation | 5
|  | Presentation Question Responses | 5
|  | Subtotal | 30 | pts
|  | Total | 100 | pts
Competition Judging Team will consist of:
WAPA Producer Members
WisDOT Staff
WAPA Staff

## Project Data
2012 WAPA Asphalt Pavement Design Competition
Project Data
Project Information:
| Highway: | STH 2012
| Location: | Town of Wapaville in Blacktop County, Wisconsin
| Project Length: | 6.8 miles (Rural highway with 2 connecting sideroads and 4 field entrances)
| Project Scope: | 2-Lane Roadway Pavement Replacement (18 year minimum service life desired)
The original pavement is a 4" HMA pavement 30' wide (including the paved shoulders) and 12" base material (CABC)
below the asphalt. A 3" HMA overlay has been applied to the pavement. This segment of highway has a
3% longitudinal grade with side slopes of 6:1 and 40 feet of right-of-way on each side of the roadway centerline. The
roadway profile may be raised a maximum of 3". The posted speed limit is 55 MPH.
A new industrial manufacturing facility (My Plant) is being built in the south west quadrant of the Fisher Road intersection.
The facility will be generating additional heavy vehicle loads that need to be addressed with this roadway construction
project.
Existing pavement history:
|  |  | 1982 | Original Construction
30' pavement width, with a 2% crown
Pav't Structure:
4" HMA
12" existing base course
|  |  | 2000 | Pavement Rehabilitation
3" HMA Overlay
Current pavement distress survey shows:
PCI (each distress survey section)= 73, 65, 78, 42, 55, 36, 82
IRI (avg for each survey section) = 83, 65, 68, 48, 56, 30, 72 in/mile
Coring of the pavement reveals that existing pavement thickness is variable (see project map for core locations).
Core depths A-J: 7.0", 8.0", 7.5", 7.0", 6.75", 7.5", 7.0", 8.25", 8.0", 7.25" (cores taken at centerline)
Pavement Structural Design:
| Traffic: | Existing Traffic Projection |  |  |  | Additional Traffic
|  | Construction Year ADT |  | 4000
|  | Design Year ADT |  | 5300
|  | Directional Factor |  | 0.5
|  | Lane Distribution Factor |  | 1
WisDOT Truck Type Distribution:
|  |  | Truck Type | %
|  |  | 2D | 0.5
|  |  | 3SU | 2.8
|  |  | 2-S1, 2-S2 | 3.2
|  |  | 3-S2 & Above | 1.2
|  |  | Double Bottom | 0.1
|  |  | Total HV | 7.8
| Soils: | Well drained soil classified as A-4 (AASHTO classification)
8' to Water Table
| Climate: | Wapaville Wisconsin has simlar climate conditions as Racine, Wisconsin.
| Design Methods: | Any of the following pavement design methods are acceptable: AASHTO '72, AASHTO '93, MEPDG, Asphalt Institute
Any of the following pavement design software programs are acceptable: WisPave, DARWin, MEPDG, SW-1
Any pavement design parameter not provided in the rules should be estimated and justified in the report.
| Design Alternatives: | Formulate multiple design options and select the preferred Design Alternative.
| Quantity Estimate: | For the selected Design Alternative, calculate plan quantities and costs. The following table of WisDOT
Bid Items are available to put the project proposal together.
Unit Wt. for
| Bid Items: | Pay Item | Description |  |  |  |  | Unit | Price | quantity calculations
|  | 204.0100 | Removing Pavement |  |  |  |  | S.Y. | 2.69
|  | 204.0120 | Removing Asphaltic Surface, Milling |  |  |  |  | S.Y. | 1.34
|  | 211.0100 | Preparation Of Foundation For Asphaltic Pavement |  |  |  |  | L.S. | 6815.83
|  | 305.0110 | Base Aggregate Dense 3/4-Inch |  |  |  |  | TON | TBD | 2 Tons / CY
|  | 305.0120 | Base Aggregate Dense 1 1/4-Inch |  |  |  |  | TON | TBD | 2 Tons / CY
|  | 325.0100 | Pulverize And Relay |  |  |  |  | S.Y. | 1.05
|  | 330.0100 | Mill And Relay |  |  |  |  | S.Y. | 1.4
|  | 335.0100 | Rubblizing |  |  |  |  | S.Y. | 2.08
|  | 340.0100 | Cracking And Seating Concrete Pavement |  |  |  |  | S.Y. | 0.67
|  | 390.0203 | Base Patching, Asphaltic |  |  |  |  | S.Y. | 24.29
|  | 390.0303 | Base Patching, Concrete |  |  |  |  | S.Y. | 42.17
|  | 455.0105 | Asphaltic Material PG 58-28 |  |  |  |  | TON | 212.19
|  | 455.0110 | Asphaltic Material PG 58-34 |  |  |  |  | TON | 396.35
|  | 455.0115 | Asphaltic Material PG 64-22 |  |  |  |  | TON | 195.42
|  | 455.0120 | Asphaltic Material PG 64-28 |  |  |  |  | TON | 273.92
|  | 455.0122 | Asphaltic Material PG 64-34 |  |  |  |  | TON | 387.12
|  | 455.0125 | Asphaltic Material PG 70-28 |  |  |  |  | TON | 437.82
|  | 455.0605 | Asphaltic Material For Tack Coat |  |  |  |  | GAL | 2.62
|  | 460.1100 | Asphaltic Concrete Pavement, Type E-0.3 |  |  |  |  | TON | 41.84 | 110 lbs / SY / in thickness
|  | 460.1101 | Asphaltic Concrete Pavement, Type E-1 |  |  |  |  | TON | TBD | 110 lbs / SY / in thickness
|  | 460.1103 | Asphaltic Concrete Pavement, Type E-3 |  |  |  |  | TON | TBD | 110 lbs / SY / in thickness
|  | 460.1110 | Asphaltic Concrete Pavement, Type E-10 |  |  |  |  | TON | TBD | 110 lbs / SY / in thickness
|  | 460.1130 | Asphaltic Concrete Pavement, Type E-30 |  |  |  |  | TON | TBD | 110 lbs / SY / in thickness
|  | 460.4200.S | HMA Pavement Intersections |  |  |  |  | TON | TBD | (Mainline Cost/ton + $15/ton)
Base course aggregate costs:
All Stockpiled aggregate material cost is $6.00/Ton (without trucking to job site)
All aggregate sources have crushing capabilities:
Production Rate = 500 tons per hour @ $2500/hr
Production is limited to weekdays from 9:00 am to 4:00 pm
Aggregate Trucking cost is $50/hr per truck
Job Mix Formula Design:
| JMF: | Following WisDOT HMA pavement construction guidelines, the HMA pavement structure consists of two mix
designs (a lower layer mix and a surface mix). For the WAPA Asphalt Pavement Design Competition,
develop an appropriate job mix formula (JMF) for the surface layer that meets WisDOT specifications.
The JMF can be developed using either the SuperPave or Bailey mix design concepts, but must conform to WisDOT 1559
Procedure (see reference). Exclude all TSR testing requirements.
Materials
| Aggregates: | For this project, there are three possible aggregates sources:
|  | 1 | My Rock Pit
Located in the middle of the project
Aggregate Source properties (as identified in WisDOT's Aggregate Source Report):
|  |  |  | LA Wear (100/500) | 15/40
|  |  |  | Soundness | 10
|  |  |  | Freeze/Thaw | 12
Base Course Stockpile:
|  |  |  | 3/4" 45,000 Tons |  |  | 1 1/4" 30,000 Tons
|  | 2 | County Quarry
Located 4.2 miles from the project
Aggregate Source properties (as identified in WisDOT's Aggregate Source Report):
|  |  |  | LA Wear (100/500) | 9/35
|  |  |  | Soundness | 12
|  |  |  | Freeze/Thaw | 15
Base Course Stockpile:
|  |  |  | 3/4" 60,000 Tons |  |  | 1 1/4" 30,000 Tons
|  | 3 | Wapaville Quarry
Located 4.5 miles from the project
Aggregate Source properties (as identified in WisDOT's Aggregate Source Report):
|  |  |  | LA Wear (100/500) | 5/20
|  |  |  | Soundness | 10
|  |  |  | Freeze/Thaw | 9
Base Course Stockpile:
|  |  |  | 3/4" 90,000 Tons |  |  | 1 1/4" 80,000 Tons
All aggregate sources have adequate asphalt mixture aggregate stockpiles and provide the same mix components
with the following parameters:
Bulk
|  |  | Material | Cost | Specific
|  |  | Component | $/Ton | Gravity | Absorption
|  |  | 5/8" Chip | 4.5 | 2.679 | 1.6
|  |  | Man. Sand | 7.5 | 2.659 | 2.2
|  |  | Nat'l Sand | 6 | 2.654 | 1.2
|  |  | RAP | 5 | 2.645 | 1
| Liquid Asphalt: | Any PG grade of asphalt my be used as long as it meets WisDOT specifications and requirements.
Clearly identify and document the use of any liquid asphalt additive or modifier used and also include
their cost in your proposal.
Construction Management:
| Scope: | Calculate a unit (TON) bid price for all of the HMA pavement mixture (assume the lower layer cost is the same as
the upper layer) that includes QMP Mixture, Pilot HMA Nuclear Density and QMP Ride (all of which are incidental
to the mixture), general overhead and profit. Itemize all equipment and personnel used. Develop a QMP Mixture testing plan,
a QMP Nuclear Density testing plan and a Construction Schedule for paving.
Develop a complete project Construction Schedule, Quantity Table and Project Proposal Bid for your selected Design/Build
pavement design alternative.
| Contract Parameters: | Contract allows for 20 Contract Days for all pavement structure work.
All paving must be done between 7:00 AM and 7:00 PM.
No work allowed on Sunday. Work zones are limited to one lane of traffic for 2.5 miles in length (max.).
Both lanes must be open to traffic when work crews are not present.
| Facilities: | HMA plant will be located at the selected aggregate source location.
HMA plant will be solely designated for this project.
Normal plant capacity is 450 tons per hour.
| HMA Mix Labor: | (Plant operator, plant end loader operator, QMP technicians, paving crew members, roller operators, trucking, flagging)
All Labor Rates:
|  |  | 1st 40 hrs per week |  | $48.00 per hour (includes time, materials, equipment)
|  |  | Hours beyond 40/week |  | $65.00 per hour (includes time, materials, equipment)
| Other Bid Item Labor: | Labor is included in the item unit price unless stated otherwise.
WisDOT References: (All WisDOT references are available on their website http://www.dot.wisconsin.gov/business/engrserv/ )
Facilities Development Manual (FDM)
|  | Chp 11 | Design
|  | Chp 14 | Pavements
Construction and Materials Manual (CMM)
|  | Chp 4 | Pavements
|  | Chp 8 | Materials Testing, Sampling and Acceptance
WisDOT 1559
Standard Specifications
Spec
Quality Management Program (QMP) Special Provisions
QMP Ride
Pilot HMA Nuclear Density

## Competition Timeline
2012 WAPA Asphalt Pavement Design Competition
Competition Timeline
Date | Task
2012-02-27 | Competition participants receive competition Rules
2012-03-12 | Final day to register Project Teams and Members with WAPA
Contact WAPA via email (scot@wispave.org)
2012-04-02 | Final day for WAPA to receive SGC specimen submission
Submit two (2) final mix design Superpave gyratory compactor (SGC) samples along
with their SGC compaction data and job mix formula (JMF)
One sample may be used for pavement performance testing
One sample may be used for mix design verification
Mailing Address:
WAPA, Scot Schwandt
620 Water Street, Suite A
Prairie du Sac, WI 53578
2012-04-20 | Final day to submit Final written report to WAPA via email (scot@wispave.org)
2012-04-20 | Final day to schedule time slot for project proposal presentation
Contact WAPA via email (scot@wispave.org)
Presentation schedule will be filled on a first come first serve basis
2012-04-27 | Project Proposal Presentation
Create and submit a PowerPoint presentation of your project proposal
Present project proposal and respond to judging questions (~1 hour)
Presentations will be presented using web conferencing
via "GoToMeeting" and conference calling
Will need a computer with internet access and the ability to download and
install "GoToMeeting" software
Will need a phone
Presentation Schedule: Friday, April 27, 2012
9:00
10:30
0:30
14:00
15:30

## Report & Presentation Outline
2012 WAPA Asphalt Design Report & Presentation Outline
(Key competition deliverables highlighted in bold green)
| I | Executive Summary
|  | i | Project Scope
Identify: Highway project type, project objective, analyzed pavement design alternatives, etc.
|  | ii | Pavement Structure Design
Final Plan X-Section (labeling: dimensions, materials, thicknesses)
Schedule of Bid Items & Estimated Quantities
|  | iii | Project Job Mix Formula
WisDOT 1559 Mix Design Report (CMM 8.65.5.4)
SGC Specimens
HMA Mixture Cost (Materials)
|  | iv | Construction Management
Construction Project Gantt Chart (broken down by processes/bid items)
HMA Mixture Unit Bid Item Price
Total Project Pavement Construction Cost (your Team's project bid)
| II | Introduction
|  | i | Project Team
|  | ii | Facilities Used
|  | iii | Technical Resources Used
|  | iv | Team Member Responsibilities
| III | Roadway Project Scope
|  | i | Background
|  | ii | Scope Development
|  | iii | Proposed Design Alternatives
|  | iv | Scope Selection
| IV | Pavement Structural Design
|  | i | Design Data
|  | ii | Design Process
|  | iii | Design Selection
|  | iv | Typical Plan X-Section
|  | v | Engineering Estimated Quantities
| V | Job Mix Formula Design
|  | i | Design Data / Criteria
|  | ii | Mix Design Process
|  | iii | Material Selection
|  | iv | Laboratory Testing
|  | v | Material Properties
|  | vi | JMF Design
|  | vii | Mix Cost
| VI | Construction Management
|  | i | Construction Data / Criteria
|  | ii | Construction Schedule Development
|  | iii | Labor / Equipment Estimate
|  | iv | QMP Testing Plans
|  | v | Construction Paving Schedule
|  | vi | Construction Project Gantt Chart (Pavement Structure Construction)
|  | vii | HMA Mixture Unit Price
|  | viii | Total Project Bid Price
| VII | Detailed Project Calculations